## Sprint Summary
BantAI Sprint Schedule
Agile Model, 3-week sprints. Started Jun 26, 2026. Target: defense-ready by Oct 31, 2026.
As of Jul 20, 2026: Sprint 1 complete, Sprint 2 in progress.
Sprint | Goal | Start | End | Duration | Sprint planning | Daily standups | Sprint review | Sprint retro | Status
Sprint 1 | Foundation & Core Backend | 2026-06-26 | 2026-07-16 |  |  | Every weekday, 15 min |  |  | Completed
Sprint 2 | Classification Pipeline & Mobile Inbox | 2026-07-17 | 2026-08-06 |  |  | Every weekday, 15 min |  |  | Current
Sprint 3 | Clustering, Explainability, Alerts & Campaigns | 2026-08-07 | 2026-08-27 |  |  | Every weekday, 15 min |  |  | Upcoming
Sprint 4 | Web Dashboard, Report Pipeline & Retraining | 2026-08-28 | 2026-09-17 |  |  | Every weekday, 15 min |  |  | Upcoming
Sprint 5 | Integration, Hardening & Stretch Features | 2026-09-18 | 2026-10-08 |  |  | Every weekday, 15 min |  |  | Upcoming
Sprint 6 | Testing, Limited Deployment & Defense Readiness | 2026-10-09 | 2026-10-29 |  |  | Every weekday, 15 min |  |  | Upcoming
Buffer | Buffer / defense day | 2026-10-30 | 2026-10-31 | [5 empty] | Buffer
Note: sprint review and retrospective are shown on the same day (last day of sprint), standard practice for short sprints.

## Gantt Overview
BantAI Sprint Schedule - Gantt Overview
6 sprints, 3 weeks each, Jun 26 - Oct 29, 2026, plus a 2-day buffer before the Oct 31 deadline.
Sprint | Focus / Track | Dates | Wk1 Jun 26-02 | Wk2 Jul 03-09 | Wk3 Jul 10-16 | Wk4 Jul 17-23 | Wk5 Jul 24-30 | Wk6 Jul 31-06 | Wk7 Aug 07-13 | Wk8 Aug 14-20 | Wk9 Aug 21-27 | Wk10 Aug 28-03 | Wk11 Sep 04-10 | Wk12 Sep 11-17 | Wk13 Sep 18-24 | Wk14 Sep 25-01 | Wk15 Oct 02-08 | Wk16 Oct 09-15 | Wk17 Oct 16-22 | Wk18 Oct 23-29
Sprint 1 (Completed) | Goal: Foundation & Core Backend
| Track A - Backend & Infrastructure | Jun 26 - Jul 16, 2026
Track B - AI/ML Pipeline
Track C - Mobile App
Track D - Web Dashboard
Sprint 2 (Current) | Goal: Classification Pipeline & Mobile Inbox
| Track A - Backend & Infrastructure | Jul 17 - Aug 06, 2026
Track B - AI/ML Pipeline
Track C - Mobile App
Track D - Web Dashboard
Sprint 3 (Upcoming) | Goal: Clustering, Explainability, Alerts & Campaigns
| Track A - Backend & Infrastructure | Aug 07 - Aug 27, 2026
Track B - AI/ML Pipeline
Track C - Mobile App
Track D - Web Dashboard
Sprint 4 (Upcoming) | Goal: Web Dashboard, Report Pipeline & Retraining
| Track A - Backend & Infrastructure | Aug 28 - Sep 17, 2026
Track B - AI/ML Pipeline
Track C - Mobile App
Track D - Web Dashboard
Sprint 5 (Upcoming) | Goal: Integration, Hardening & Stretch Features
| Track A - Backend & Infrastructure | Sep 18 - Oct 08, 2026
Track B - AI/ML Pipeline
Track C - Mobile App
Track D - Web Dashboard
Sprint 6 (Upcoming) | Goal: Testing, Limited Deployment & Defense Readiness
| Testing (All Tracks) | Oct 09 - Oct 29, 2026
Deployment (Track A/B)
Wrap-up (Track C/D)
Defense Prep (All)
Legend:
Track A - Backend & Infrastructure
Track B - AI/ML Pipeline
Track C - Mobile App
Track D - Web Dashboard
Testing (All Tracks)
Deployment (Track A/B)
Wrap-up (Track C/D)
Defense Prep (All)

## Sprint Backlog
BantAI Sprint Backlog
Detailed task list by sprint and track, mapped to the Jun 26 - Oct 29 schedule. Update Status as work progresses.
Sprint | Track | Backlog item | Start date | End date | Duration (days) | Status
Sprint 1 | Track A - Backend & Infrastructure | Finalize monorepo, Docker Compose (PostgreSQL, pgAdmin), and env variables | 2026-06-26 | 2026-07-16 |  | Done
Sprint 1 | Track A - Backend & Infrastructure | Resolve Prisma connection issues; commit schema for Android_Users, Contacts, SMS_Messages, Alerts, Protection_Settings, Blocked_Numbers — connectivity resolved & core tables done; Contacts, Protection_Settings, Blocked_Numbers carried to S2 | 2026-06-26 | 2026-07-16 |  | Carried to S2
Sprint 1 | Track A - Backend & Infrastructure | Scaffold NestJS project with base module structure and OpenAPI docs — scaffold + modules done; OpenAPI docs pending | 2026-06-26 | 2026-07-16 |  | Carried to S2
Sprint 1 | Track A - Backend & Infrastructure | Implement auth flow: mobile number verification + 6-digit OTP | 2026-06-26 | 2026-07-16 |  | Done
Sprint 1 | Track B - AI/ML Pipeline | Scaffold Python FastAPI service for the ML pipeline | 2026-06-26 | 2026-07-16 |  | Done
Sprint 1 | Track B - AI/ML Pipeline | Set up XLM-RoBERTa fine-tuning environment (dataset loading, SentencePiece tokenizer, 250K vocab) | 2026-06-26 | 2026-07-16 |  | Done
Sprint 1 | Track B - AI/ML Pipeline | Draft regex privacy masking layer (URL/PHONE/OTP/AMOUNT) + Unicode NFKC normalization | 2026-06-26 | 2026-07-16 |  | Done
Sprint 1 | Track C - Mobile App | Scaffold Android Studio project in Kotlin | 2026-06-26 | 2026-07-16 |  | Done
Sprint 1 | Track C - Mobile App | Build onboarding screens: Loading, Default SMS App, Allow Access, Confirm Number, Enter Code, Terms & Privacy, Profile Setup, Protected | 2026-06-26 | 2026-07-16 |  | Done
Sprint 1 | Track C - Mobile App | Wire onboarding to Track A auth API | 2026-06-26 | 2026-07-16 |  | Done
Sprint 1 | Track D - Web Dashboard | Scaffold React + Vite project | 2026-06-26 | 2026-07-16 |  | Done
Sprint 1 | Track D - Web Dashboard | Build Admin Portal login/2FA page and dashboard shell/navigation | 2026-06-26 | 2026-07-16 |  | Done
Sprint 2 | Track A - Backend & Infrastructure | Build classification API endpoint linking mobile app to ML service | 2026-07-17 | 2026-08-06 |  | Done
Sprint 2 | Track A - Backend & Infrastructure | Implement Message_Features and Classifications tables and storage logic | 2026-07-17 | 2026-08-06 |  | Done
Sprint 2 | Track A - Backend & Infrastructure | Set up documented RESTful API contract between mobile app and backend | 2026-07-17 | 2026-08-06 |  | Done
Sprint 2 | Track B - AI/ML Pipeline | Complete privacy masking + normalization pipeline | 2026-07-17 | 2026-08-06 |  | Done
Sprint 2 | Track B - AI/ML Pipeline | Fine-tune XLM-RoBERTa on Philippine smishing dataset (Tagalog/English/Taglish) | 2026-07-17 | 2026-08-06 |  | Done
Sprint 2 | Track B - AI/ML Pipeline | Implement softmax classification head (Ham / Spam / Scam) | 2026-07-17 | 2026-08-06 |  | Done
Sprint 2 | Track B - AI/ML Pipeline | Implement confidence threshold routing (>=0.90 auto-block, 0.50-0.90 alert, <0.50 inbox) | 2026-07-17 | 2026-08-06 |  | Done
Sprint 2 | Track C - Mobile App | Implement default SMS broadcast receiver | 2026-07-17 | 2026-08-06 |  | Done
Sprint 2 | Track C - Mobile App | Build Home Screen and Messages: Inbox Screen | 2026-07-17 | 2026-08-06 |  | Done
Sprint 2 | Track C - Mobile App | Build Suspicious Filter Screen and Suspicious Message Detail Screen | 2026-07-17 | 2026-08-06 |  | Done
Sprint 2 | Track C - Mobile App | Build Unsafe Link Screen and Take Action Selection Screen | 2026-07-17 | 2026-08-06 |  | Done
Sprint 2 | Track D - Web Dashboard | Build Admin Overview Page and Admin Classification Log Page | 2026-07-17 | 2026-08-06 |  | Done
Sprint 3 | Track A - Backend & Infrastructure | Implement Campaign_Cluster, Explainable_Indicator, Sender_Verification_Cache tables | 2026-08-07 | 2026-08-27 |  | Not started
Sprint 3 | Track A - Backend & Infrastructure | Build sender verification endpoint | 2026-08-07 | 2026-08-27 |  | Not started
Sprint 3 | Track A - Backend & Infrastructure | Build link suppression logic at the API layer | 2026-08-07 | 2026-08-27 |  | Not started
Sprint 3 | Track B - AI/ML Pipeline | Implement cosine similarity centroid comparison (threshold 0.85) | 2026-08-07 | 2026-08-27 |  | Not started
Sprint 3 | Track B - AI/ML Pipeline | Implement HDBSCAN offline re-clustering (min_cluster_size = 5) | 2026-08-07 | 2026-08-27 |  | Not started
Sprint 3 | Track B - AI/ML Pipeline | Integrate SHAP explainability + indicator tag mapping dictionary | 2026-08-07 | 2026-08-27 |  | Not started
Sprint 3 | Track B - AI/ML Pipeline | Build scam awareness tip lookup tied to cluster ID | 2026-08-07 | 2026-08-27 |  | Not started
Sprint 3 | Track C - Mobile App | Build Alert Screen and Suspicious Alert Screen | 2026-08-07 | 2026-08-27 |  | Not started
Sprint 3 | Track C - Mobile App | Build Campaign Screen, Active/Inactive Campaign Modal/Screen | 2026-08-07 | 2026-08-27 |  | Not started
Sprint 3 | Track C - Mobile App | Build Notifications: Threat Alert, Weekly Report, Smishing Alert, Weekly Alert | 2026-08-07 | 2026-08-27 |  | Not started
Sprint 3 | Track C - Mobile App | Build Settings: Scam Awareness Tips Screen and Tip Details Screen | 2026-08-07 | 2026-08-27 |  | Not started
Sprint 3 | Track D - Web Dashboard | Build Admin Concept Drift Page and Admin Campaign / Campaign Timeline Page | 2026-08-07 | 2026-08-27 |  | Not started
Sprint 3 | Track D - Web Dashboard | Build Admin Dataset Management Page | 2026-08-07 | 2026-08-27 |  | Not started
Sprint 4 | Track A - Backend & Infrastructure | Implement report feedback pipeline (UserReports -> admin validate/reject -> training dataset) | 2026-08-28 | 2026-09-17 |  | Not started
Sprint 4 | Track A - Backend & Infrastructure | Implement hourly retraining trigger check (sample count, F1 drop, Page-Hinkley drift) | 2026-08-28 | 2026-09-17 |  | Not started
Sprint 4 | Track A - Backend & Infrastructure | Implement ModelVersions table and promotion/rollback logic | 2026-08-28 | 2026-09-17 |  | Not started
Sprint 4 | Track B - AI/ML Pipeline | Build automated retraining workflow (snapshot, AdamW fine-tune, reservoir update, McNemar/F1 gate) | 2026-08-28 | 2026-09-17 |  | Not started
Sprint 4 | Track B - AI/ML Pipeline | Build campaign evolution tracking logic | 2026-08-28 | 2026-09-17 |  | Not started
Sprint 4 | Track B - AI/ML Pipeline | Implement TF-IDF extractive summarization for unread threads | 2026-08-28 | 2026-09-17 |  | Not started
Sprint 4 | Track C - Mobile App | Build Compose Message Screen and Unknown Filter Screen | 2026-08-28 | 2026-09-17 |  | Not started
Sprint 4 | Track C - Mobile App | Build AI Message Summary display | 2026-08-28 | 2026-09-17 |  | Not started
Sprint 4 | Track C - Mobile App | Build Settings: Blocked Numbers Screen | 2026-08-28 | 2026-09-17 |  | Not started
Sprint 4 | Track D - Web Dashboard | Build Admin User Reports, FP/FN Review, Model Performance Pages | 2026-08-28 | 2026-09-17 |  | Not started
Sprint 4 | Track D - Web Dashboard | Build Admin Registered Users, Export Hub, Server Monitoring, API Logs, DB Storage Pages | 2026-08-28 | 2026-09-17 |  | Not started
Sprint 4 | Track D - Web Dashboard | Build Admin Scam Tips, Settings, Notifications Pages | 2026-08-28 | 2026-09-17 |  | Not started
Sprint 5 | Track A - Backend & Infrastructure | End-to-end integration hardening across mobile, backend, and dashboard | 2026-09-18 | 2026-10-08 |  | Not started
Sprint 5 | Track A - Backend & Infrastructure | Security and performance pass on all API endpoints | 2026-09-18 | 2026-10-08 |  | Not started
Sprint 5 | Track A - Backend & Infrastructure | Add manual retraining trigger as fallback if automated trigger is unstable | 2026-09-18 | 2026-10-08 |  | Not started
Sprint 5 | Track B - AI/ML Pipeline | Refine XLM-RoBERTa using data collected through Sprints 2-4 | 2026-09-18 | 2026-10-08 |  | Not started
Sprint 5 | Track B - AI/ML Pipeline | Re-evaluate HDBSCAN clustering thresholds against real campaign data | 2026-09-18 | 2026-10-08 |  | Not started
Sprint 5 | Track B - AI/ML Pipeline | Polish SHAP indicator tag dictionary based on observed outputs | 2026-09-18 | 2026-10-08 |  | Not started
Sprint 5 | Track C - Mobile App | Bug bash: unusual sender formats, mixed-language edge cases, low-end device performance | 2026-09-18 | 2026-10-08 |  | Not started
Sprint 5 | Track C - Mobile App | UI polish based on internal dogfooding | 2026-09-18 | 2026-10-08 |  | Not started
Sprint 5 | Track D - Web Dashboard | (Stretch) Client licensing/payment portal pages, if time allows | 2026-09-18 | 2026-10-08 |  | Not started
Sprint 5 | Track D - Web Dashboard | Admin UX polish; finish any dashboard pages not completed in Sprint 4 | 2026-09-18 | 2026-10-08 |  | Not started
Sprint 6 | Testing (All Tracks) | Unit testing: preprocessing, classification, sender verification, link suppression, threshold mapping, summarization, tips, report feedback, storage | 2026-10-09 | 2026-10-29 |  | Not started
Sprint 6 | Testing (All Tracks) | Integration testing across mobile, backend, database, AI model, dashboard | 2026-10-09 | 2026-10-29 |  | Not started
Sprint 6 | Testing (All Tracks) | System testing: full end-to-end SMS-to-output flow | 2026-10-09 | 2026-10-29 |  | Not started
Sprint 6 | Testing (All Tracks) | User Acceptance Testing with 20 general Android users | 2026-10-09 | 2026-10-29 |  | Not started
Sprint 6 | Testing (All Tracks) | Expert Validation with 5 IT/cybersecurity/software professionals | 2026-10-09 | 2026-10-29 |  | Not started
Sprint 6 | Testing (All Tracks) | False positive / false negative confusion matrix review | 2026-10-09 | 2026-10-29 |  | Not started
Sprint 6 | Deployment (Track A/B) | Distribute app via APK to test group and administrators (Phase 1: Limited Deployment) | 2026-10-09 | 2026-10-29 |  | Not started
Sprint 6 | Deployment (Track A/B) | Confirm real-time integration stability under live SMS conditions | 2026-10-09 | 2026-10-29 |  | Not started
Sprint 6 | Deployment (Track A/B) | Track precision, recall, F1 against test-group error reports | 2026-10-09 | 2026-10-29 |  | Not started
Sprint 6 | Wrap-up (Track C/D) | Bug fixes and refinements from testing | 2026-10-09 | 2026-10-29 |  | Not started
Sprint 6 | Wrap-up (Track C/D) | Finalize quick-start guide | 2026-10-09 | 2026-10-29 |  | Not started
Sprint 6 | Wrap-up (Track C/D) | Polish UI issues flagged during UAT | 2026-10-09 | 2026-10-29 |  | Not started
Sprint 6 | Defense Prep (All) | Finalize manuscript sections affected by implementation changes | 2026-10-09 | 2026-10-29 |  | Not started
Sprint 6 | Defense Prep (All) | Prepare and rehearse live demo | 2026-10-09 | 2026-10-29 |  | Not started
Sprint 6 | Defense Prep (All) | Prepare defense slide deck | 2026-10-09 | 2026-10-29 |  | Not started