## WBS
Work Breakdown Structure (WBS)
|  | Project Name | BantAI - AI-Based Campaign Intelligence and Incoming SMS Triage System |  |  | Project ID: | THESONE-Group-7 |  | Date: | 2026-08-16
|  | Project Manager: | [6 empty] | Version: | 1.0
Task ID | Task Description | Dependent Upon | Task Owner | Resource Required | Task Status | Estimated Cost | Start Date | Planned Completion Date | Actual Completion Date | Additional Information
1 | Sprint 1: Foundation & Core Backend |  | All members | Sprint backlog, Chapter 3 pseudocode & mockups | Complete | - | 2026-06-26 | 2026-07-16 | 2026-07-16 | 3-week sprint per Agile Model
1.1 | Analysis: refine backlog for Sprint 1, clarify acceptance criteria. [Analysis] |  | All members | Per work-package resources listed below | Complete | - | 2026-06-26 | 2026-07-16 | 2026-07-16
1.1.1 | Confirm scope of core backend, database, and app scaffold for Sprint 1 |  | All members | Thesis Chapter 3, use case diagram | Complete | - | 2026-06-26 | 2026-07-16 | 2026-07-16 | Backlog refinement session
1.1.2 | Finalize Prisma schema requirements for core tables |  | Track A (Backend) | Class diagram (Fig. 3), database design (Fig. 5) | Complete | - | 2026-06-26 | 2026-07-16 | 2026-07-16
1.2 | Design: technical specifications and interface designs for Sprint 1 items. [Design] |  | Assigned per WP | Per work-package resources listed below | Complete | - | 2026-06-26 | 2026-07-16 | 2026-07-16
1.2.1 | Monorepo structure design | 1.1.1 | All members | Repository conventions doc | Complete | - | 2026-06-26 | 2026-07-16 | 2026-07-16
1.2.2 | Docker Compose service topology | 1.1.2 | Track A (Backend) | docker-compose reference | Complete | - | 2026-06-26 | 2026-07-16 | 2026-07-16
1.2.3 | NestJS module layout | 1.1.2 | Track A (Backend) | NestJS docs | Complete | - | 2026-06-26 | 2026-07-16 | 2026-07-16
1.2.4 | Onboarding UX flow spec |  | Track C (Mobile) | UI mockups (Fig. 7-14) | Complete | - | 2026-06-26 | 2026-07-16 | 2026-07-16
1.3 | Build (development): implement the Sprint 1 work packages. [Build] |  | Assigned per WP | Per work-package resources listed below | Complete | - | 2026-06-26 | 2026-07-16 | 2026-07-16
1.3.1 | Monorepo scaffold | 1.2.1 | All members | Node.js, npm | Complete | - | 2026-06-26 | 2026-07-16 | 2026-07-16
1.3.2 | Docker Compose: PostgreSQL + pgAdmin services | 1.2.2 | Track A (Backend) | Docker Desktop | Complete | - | 2026-06-26 | 2026-07-16 | 2026-07-16
1.3.3 | Environment variables & secrets | 1.3.2 | Track A (Backend) | .env, dotenv | Complete | - | 2026-06-26 | 2026-07-16 | 2026-07-16
1.3.4 | Prisma schema: Android_Users, Contacts, SMS_Messages, Alerts, Protection_Settings, Blocked_Numbers | 1.3.2 | Track A (Backend) | Prisma, PostgreSQL | Complete | - | 2026-06-26 | 2026-07-16 | 2026-07-16 | Committed: Android_Users, SMS_Messages, Alerts, Classification. Contacts, Protection_Settings, Blocked_Numbers not yet committed — carried to Sprint 2.
1.3.5 | NestJS project scaffold + OpenAPI setup | 1.2.3 | Track A (Backend) | NestJS, Swagger | Complete | - | 2026-06-26 | 2026-07-16 | 2026-07-16 | NestJS scaffold + base modules done. OpenAPI/Swagger not yet wired (no @nestjs/swagger dependency) — carried to Sprint 2.
1.3.6 | Authentication endpoints (mobile number + 6-digit OTP) | 1.3.5 | Track A (Backend) | NestJS Auth, SMS gateway sandbox | Complete | - | 2026-06-26 | 2026-07-16 | 2026-07-16
1.3.7 | FastAPI ML service scaffold |  | Track B (AI/ML) | Python 3.11, FastAPI | Complete | - | 2026-06-26 | 2026-07-16 | 2026-07-16
1.3.8 | XLM-RoBERTa fine-tuning environment (dataset loading, SentencePiece) | 1.3.7 | Track B (AI/ML) | PyTorch, HuggingFace Transformers, GPU access | Complete | - | 2026-06-26 | 2026-07-16 | 2026-07-16
1.3.9 | Draft regex privacy masking (URL/PHONE/OTP/AMOUNT) + NFKC | 1.3.7 | Track B (AI/ML) | Python re, unicodedata | Complete | - | 2026-06-26 | 2026-07-16 | 2026-07-16
1.3.10 | Android Studio project (Kotlin) | 1.2.4 | Track C (Mobile) | Android Studio, Kotlin | Complete | - | 2026-06-26 | 2026-07-16 | 2026-07-16
1.3.11 | Onboarding screens (8 screens: Loading, Default SMS App, Allow Access, Confirm Number, Enter Code, Terms & Privacy, Profile Setup, Protected) | 1.3.10 | Track C (Mobile) | Jetpack Compose | Complete | - | 2026-06-26 | 2026-07-16 | 2026-07-16
1.3.12 | React + Vite dashboard scaffold + Admin 2FA page | 1.3.6 | Track D (Web Dashboard) | React + Vite, TypeScript | Complete | - | 2026-06-26 | 2026-07-16 | 2026-07-16
1.4 | Test: sprint-level unit and integration testing before demo. [Test] |  | Assigned per WP | Per work-package resources listed below | Complete | - | 2026-06-26 | 2026-07-16 | 2026-07-16
1.4.1 | Smoke test: end-to-end onboarding + auth flow | 1.3.11, 1.3.6 | All members | Test devices, test SMS gateway | Complete | - | 2026-06-26 | 2026-07-16 | 2026-07-16
1.4.2 | Smoke test: Prisma migrations apply cleanly | 1.3.4 | Track A (Backend) | Fresh PostgreSQL instance | Complete | - | 2026-06-26 | 2026-07-16 | 2026-07-16
1.5 | Sprint Review (demo) and Retrospective (lessons learned) at end of Sprint 1. [Review + Retro] |  | All members | Per work-package resources listed below | Complete | - | 2026-06-26 | 2026-07-16 | 2026-07-16
1.5.1 | Sprint 1 demo (working onboarding + DB up) | 1.4.1, 1.4.2 | All members | Meeting room / call | Complete | - | 2026-06-26 | 2026-07-16 | 2026-07-16
1.5.2 | Sprint 1 retrospective (what went well, what to improve) |  | All members | Retro board (Miro/paper) | Complete | - | 2026-06-26 | 2026-07-16 | 2026-07-16 | Outputs feed Sprint 2 planning
2 | Sprint 2: Classification Pipeline & Mobile Inbox |  | All members | Sprint backlog, Chapter 3 pseudocode & mockups | Complete | - | 2026-07-17 | 2026-08-06 | 2026-08-07 | 3-week sprint per Agile Model
2.1 | Analysis: refine backlog for Sprint 2, clarify acceptance criteria. [Analysis] |  | All members | Per work-package resources listed below | Complete | - | 2026-07-17 | 2026-08-06 | 2026-08-07
2.1.1 | Refine classification pipeline requirements |  | All members | Algorithm interaction diagram (Fig. 88) | Complete | - | 2026-07-17 | 2026-08-06 | 2026-08-07
2.1.2 | Confirm confidence-threshold routing rules (0.90 / 0.50) |  | Track B (AI/ML) | Chapter 3 threshold routing section | Complete | - | 2026-07-17 | 2026-08-06 | 2026-08-07
2.2 | Design: technical specifications and interface designs for Sprint 2 items. [Design] |  | Assigned per WP | Per work-package resources listed below | Complete | - | 2026-07-17 | 2026-08-06 | 2026-08-07
2.2.1 | SMS ingestion API contract | 2.1.1 | Track A (Backend) | OpenAPI spec | Complete | - | 2026-07-17 | 2026-08-06 | 46224 | Completed via PR #12 (SMS ingestion endpoint, MessageFeature model, API contract docs/api/sms.md).
2.2.2 | Classification service API design | 2.1.1 | Track B (AI/ML) | FastAPI service structure | Complete | - | 2026-07-17 | 2026-08-06 | 2026-08-07
2.2.3 | Mobile inbox information architecture |  | Track C (Mobile) | Mockups (Fig. 15-22) | Complete | - | 2026-07-17 | 2026-08-06 | 2026-08-07
2.3 | Build (development): implement the Sprint 2 work packages. [Build] |  | Assigned per WP | Per work-package resources listed below | Complete | - | 2026-07-17 | 2026-08-06 | 2026-08-07
2.3.1 | Classification API endpoint (NestJS) | 2.2.1 | Track A (Backend) | NestJS, Prisma | Complete | - | 2026-07-17 | 2026-08-06 | 46224 | Completed via PR #12 (SMS ingestion endpoint, MessageFeature model, API contract docs/api/sms.md).
2.3.2 | Message_Features + Classifications tables (Prisma models) | 1.3.4 | Track A (Backend) | Prisma | Complete | - | 2026-07-17 | 2026-08-06 | 46224 | Completed via PR #12 (SMS ingestion endpoint, MessageFeature model, API contract docs/api/sms.md).
2.3.3 | Complete privacy masking + NFKC pipeline | 1.3.9 | Track B (AI/ML) | Python re, unicodedata | Complete | - | 2026-07-17 | 2026-08-06 | 46222 | Completed Sprint 2 deliverable; awaiting labeled dataset for training.
2.3.4 | Fine-tune XLM-RoBERTa on Philippine smishing dataset (80/20 split) | 1.3.8, 2.3.3 | Track B (AI/ML) | Kaggle datasets + NTC/CICC data, GPU | Complete | - | 2026-07-17 | 2026-08-06 | 2026-08-07 | Combined 4 Kaggle sources
2.3.5 | Softmax classification head (Ham / Spam / Scam) | 2.3.4 | Track B (AI/ML) | PyTorch | Complete | - | 2026-07-17 | 2026-08-06 | 46222 | Completed Sprint 2 deliverable; awaiting labeled dataset for training.
2.3.6 | Confidence threshold routing (>=0.90 auto-block, 0.50-0.90 alert, <0.50 inbox) | 2.3.5 | Track B (AI/ML) | Backend integration | Complete | - | 2026-07-17 | 2026-08-06 | 46222 | Completed Sprint 2 deliverable; awaiting labeled dataset for training.
2.3.7 | Android SMS broadcast receiver (default SMS app) | 1.3.10 | Track C (Mobile) | Android SMS APIs | Complete | - | 2026-07-17 | 2026-08-06
2.3.8 | Home Screen + Messages: Inbox screens | 2.3.7 | Track C (Mobile) | Jetpack Compose | Complete | - | 2026-07-17 | 2026-08-06
2.3.9 | Suspicious Filter + Suspicious Message Detail screens | 2.3.8 | Track C (Mobile) | Jetpack Compose | Complete | - | 2026-07-17 | 2026-08-06
2.3.10 | Unsafe Link + Take Action Selection screens | 2.3.8 | Track C (Mobile) | Jetpack Compose | Complete | - | 2026-07-17 | 2026-08-06
2.3.11 | Admin Overview + Classification Log pages | 1.3.13 | Track D (Web Dashboard) | React + Vite, TanStack Table | Complete | - | 2026-07-17 | 2026-08-06
2.4 | Test: sprint-level unit and integration testing before demo. [Test] |  | Assigned per WP | Per work-package resources listed below | Complete | - | 2026-07-17 | 2026-08-06 | 2026-08-07
2.4.1 | Unit test: privacy masking & NFKC normalization | 2.3.3 | Track B (AI/ML) | pytest | Complete | - | 2026-07-17 | 2026-08-06 | 2026-08-07
2.4.2 | Unit test: threshold routing boundary cases | 2.3.6 | Track B (AI/ML) | pytest | Complete | - | 2026-07-17 | 2026-08-06 | 2026-08-07
2.4.3 | Integration test: mobile -> backend -> ML service round trip | 2.3.11 | All members | Test SMS, test device | Complete | - | 2026-07-17 | 2026-08-06 | 2026-08-07
2.5 | Sprint Review (demo) and Retrospective (lessons learned) at end of Sprint 2. [Review + Retro] |  | All members | Per work-package resources listed below | Complete | - | 2026-07-17 | 2026-08-06 | 2026-08-07
2.5.1 | Sprint 2 demo (live SMS -> classification -> inbox routing) | 2.4.3 | All members | Test device with sample SMS | Complete | - | 2026-07-17 | 2026-08-06 | 2026-08-07
2.5.2 | Sprint 2 retrospective |  | All members | Retro board | Complete | - | 2026-07-17 | 2026-08-06 | 2026-08-07
3 | Sprint 3: Clustering, Explainability, Alerts & Campaigns |  | All members | Sprint backlog, Chapter 3 pseudocode & mockups | Complete | - | 2026-08-07 | 2026-08-27 | 2026-08-07 | 3-week sprint per Agile Model
3.1 | Analysis: refine backlog for Sprint 3, clarify acceptance criteria. [Analysis] |  | All members | Per work-package resources listed below | Complete | - | 2026-08-07 | 2026-08-27 | 2026-08-07
3.1.1 | Refine clustering + explainability requirements |  | All members | Fig. 88 pipeline | Complete | - | 2026-08-07 | 2026-08-27 | 2026-08-07
3.1.2 | Confirm SHAP indicator tag dictionary contents |  | Track B (AI/ML) | Manuscript indicator examples (Prize Lure, Suspicious URL, etc.) | Complete | - | 2026-08-07 | 2026-08-27 | 2026-08-07
3.2 | Design: technical specifications and interface designs for Sprint 3 items. [Design] |  | Assigned per WP | Per work-package resources listed below | Complete | - | 2026-08-07 | 2026-08-27 | 2026-08-07
3.2.1 | Campaign clustering data flow spec | 3.1.1 | Track B (AI/ML) | Manuscript pseudocode | Complete | - | 2026-08-07 | 2026-08-27 | 2026-08-07
3.2.2 | Explainability output format for mobile & dashboard |  | Track B (AI/ML) | SHAP output schema | Complete | - | 2026-08-07 | 2026-08-27 | 2026-08-07
3.2.3 | Alerts + Campaigns mobile UX spec |  | Track C (Mobile) | Mockups (Fig. 35-42) | Complete | - | 2026-08-07 | 2026-08-27 | 2026-08-07
3.3 | Build (development): implement the Sprint 3 work packages. [Build] |  | Assigned per WP | Per work-package resources listed below | Complete | - | 2026-08-07 | 2026-08-27 | 2026-08-07
3.3.1 | Campaign_Cluster + Explainable_Indicator + Sender_Verification_Cache tables | 1.3.4 | Track A (Backend) | Prisma | Complete | - | 2026-08-07 | 2026-08-27 | 2026-08-07
3.3.2 | Sender verification endpoint | 3.3.1 | Track A (Backend) | NestJS | Complete | - | 2026-08-07 | 2026-08-27 | 2026-08-07
3.3.3 | Link suppression API logic | 3.3.1 | Track A (Backend) | URL detection library | Complete | - | 2026-08-07 | 2026-08-27 | 2026-08-07
3.3.4 | Cosine similarity module (threshold 0.85 against active centroids) | 2.3.4 | Track B (AI/ML) | NumPy, scikit-learn | Complete | - | 2026-08-07 | 2026-08-27 | 2026-08-07
3.3.5 | HDBSCAN offline re-clustering (min_cluster_size = 5) | 3.3.4 | Track B (AI/ML) | hdbscan library | Complete | - | 2026-08-07 | 2026-08-27 | 2026-08-07
3.3.6 | SHAP integration + indicator tag mapping via curated dictionary | 2.3.5 | Track B (AI/ML) | shap library | Complete | - | 2026-08-07 | 2026-08-27 | 2026-08-07
3.3.7 | Scam awareness tip lookup by cluster ID | 3.3.5 | Track B (AI/ML) | Tip content database | Complete | - | 2026-08-07 | 2026-08-27 | 2026-08-07
3.3.8 | Alert Screen + Suspicious Alert Screen | 2.3.7 | Track C (Mobile) | Jetpack Compose | Complete | - | 2026-08-07 | 2026-08-27 | 2026-08-07
3.3.9 | Campaign Screen + Active/Inactive Campaign screens + Modal | 3.3.5 | Track C (Mobile) | Jetpack Compose | Complete | - | 2026-08-07 | 2026-08-27 | 2026-08-07
3.3.10 | Notification screens (Threat Alert, Weekly Report, Smishing Alert, Weekly Alert) |  | Track C (Mobile) | Android Notifications API | Complete | - | 2026-08-07 | 2026-08-27 | 2026-08-07
3.3.11 | Settings: Scam Awareness Tips + Tip Details screens | 3.3.7 | Track C (Mobile) | Jetpack Compose | Complete | - | 2026-08-07 | 2026-08-27 | 2026-08-07
3.3.12 | Admin Concept Drift + Campaign + Campaign Timeline pages | 1.3.13 | Track D (Web Dashboard) | React + Vite, Chart.js | Complete | - | 2026-08-07 | 2026-08-27 | 2026-08-07
3.3.13 | Admin Dataset Management page | 1.3.13 | Track D (Web Dashboard) | React + Vite, TanStack Table | Complete | - | 2026-08-07 | 2026-08-27 | 2026-08-07
3.4 | Test: sprint-level unit and integration testing before demo. [Test] |  | Assigned per WP | Per work-package resources listed below | Complete | - | 2026-08-07 | 2026-08-27 | 2026-08-07
3.4.1 | Unit test: cosine similarity threshold logic | 3.3.4 | Track B (AI/ML) | pytest | Complete | - | 2026-08-07 | 2026-08-27 | 2026-08-07
3.4.2 | Unit test: HDBSCAN grouping stability | 3.3.5 | Track B (AI/ML) | pytest | Complete | - | 2026-08-07 | 2026-08-27 | 2026-08-07
3.4.3 | Integration test: SHAP output flows from ML service to mobile display | 3.3.6, 3.3.9 | All members | Test devices | Complete | - | 2026-08-07 | 2026-08-27 | 2026-08-07
3.5 | Sprint Review (demo) and Retrospective (lessons learned) at end of Sprint 3. [Review + Retro] |  | All members | Per work-package resources listed below | Complete | - | 2026-08-07 | 2026-08-27 | 2026-08-07
3.5.1 | Sprint 3 demo (grouped campaign alert with explainable indicators) | 3.4.3 | All members | Test devices, sample campaign SMS | Complete | - | 2026-08-07 | 2026-08-27 | 2026-08-07
3.5.2 | Sprint 3 retrospective |  | All members | Retro board | Complete | - | 2026-08-07 | 2026-08-27 | 2026-08-07
4 | Sprint 4: Web Dashboard, Report Pipeline & Retraining |  | All members | Sprint backlog, Chapter 3 pseudocode & mockups | In Progress | - | 2026-08-28 | 2026-09-17 |  | 3-week sprint per Agile Model (Chapter 3)
4.1 | Analysis: refine backlog for Sprint 4, clarify acceptance criteria. [Analysis] |  | All members | Per work-package resources listed below | In Progress | - | 2026-08-28 | 2026-09-17
4.1.1 | Refine report feedback pipeline requirements |  | All members | Manuscript pseudocode | Not Started | - | 2026-08-28 | 2026-09-17
4.1.2 | Confirm retraining trigger thresholds (50 samples, F1 drop 5%, Page-Hinkley) |  | Track B (AI/ML) | Chapter 3 retraining section | Complete | - | 2026-08-28 | 2026-09-17 | 2026-08-07
4.2 | Design: technical specifications and interface designs for Sprint 4 items. [Design] |  | Assigned per WP | Per work-package resources listed below | Complete | - | 2026-08-28 | 2026-09-17 | 2026-08-12
4.2.1 | Report feedback state machine (Pending / Validated / Rejected / Resolved) | 4.1.1 | Track A (Backend) | State diagram | Not Started | - | 2026-08-28 | 2026-09-17
4.2.2 | Retraining workflow architecture | 4.1.2 | Track B (AI/ML) | Manuscript workflow spec | Complete | - | 2026-08-28 | 2026-09-17 | 2026-08-07
4.2.3 | Model promotion + rollback design | 4.1.2 | Track B (AI/ML) | ModelVersions schema | Complete | - | 2026-08-28 | 2026-09-17 | 2026-08-07
4.3 | Build (development): implement the Sprint 4 work packages. [Build] |  | Assigned per WP | Per work-package resources listed below | In Progress | - | 2026-08-28 | 2026-09-17
4.3.1 | UserReports table + report intake endpoint | 1.3.4 | Track A (Backend) | Prisma, NestJS | Complete | - | 2026-08-28 | 2026-09-17 | 2026-08-12
4.3.2 | Admin validate/reject endpoints | 4.3.1 | Track A (Backend) | NestJS | Complete | - | 2026-08-28 | 2026-09-17 | 2026-08-12
4.3.3 | Hourly retraining trigger service (cron) | 4.3.2 | Track A (Backend) | @nestjs/schedule | Complete | - | 2026-08-28 | 2026-09-17 | 2026-08-12
4.3.4 | ModelVersions table + promotion/rollback logic | 1.3.4 | Track A (Backend) | Prisma | Complete | - | 2026-08-28 | 2026-09-17 | 2026-08-12
4.3.5 | Automated retraining pipeline (snapshot + AdamW fine-tune) | 2.3.4, 4.3.3 | Track B (AI/ML) | PyTorch, GPU | Not Started | - | 2026-08-28 | 2026-09-17
4.3.6 | Reservoir sampling (Vitter's Algorithm R) | 4.3.5 | Track B (AI/ML) | NumPy | Complete | - | 2026-08-28 | 2026-09-17 | 2026-08-07
4.3.7 | McNemar test + F1 floor promotion gate | 4.3.5 | Track B (AI/ML) | SciPy stats | Complete | - | 2026-08-28 | 2026-09-17 | 2026-08-07
4.3.8 | Campaign evolution tracking | 3.3.5 | Track B (AI/ML) | Time-series over clusters | In Progress | - | 2026-08-28 | 2026-09-17
4.3.9 | TF-IDF summarization pipeline (unread threads) |  | Track B (AI/ML) | scikit-learn TF-IDF | Complete | - | 2026-08-28 | 2026-09-17 | 2026-08-07 | Independent pipeline
4.3.10 | Compose Message + Unknown Filter screens | 2.3.7 | Track C (Mobile) | Jetpack Compose | Complete | - | 2026-08-28 | 2026-09-17 | 2026-08-16 | Unknown Filter built: MessageFilter.UNKNOWN added to MessagesViewModel.kt, wired into MessagesScreen.kt's filter dropdown. compileDebugKotlin passes. Merged to develop via PR #46 (bc30c48).
4.3.11 | AI Message Summary display | 4.3.9 | Track C (Mobile) | Consumes 4.3.9 | Complete | - | 2026-08-28 | 2026-09-17 | 2026-08-16 | Now real end to end: new POST /api/ai/summarize backend proxy (JWT-guarded) forwards to the AI service's existing /summarize; new SummarizeApi.kt calls it from MessageDetailScreen.kt; AISummaryBottomSheet.kt renders the real summary and the fabricated 68%/92% confidence line was removed. Backend 167/167 tests pass. compileDebugKotlin passes. Merged to develop via PR #46 (bc30c48).
4.3.12 | Settings: Blocked Numbers screen | 1.3.11 | Track C (Mobile) | Jetpack Compose | Complete | - | 2026-08-28 | 2026-09-17 | 2026-08-16 | Now synced both directions: new backend BlockedNumbersModule (GET/POST /api/blocked-numbers, DELETE /api/blocked-numbers/:sender); BlockedNumbersViewModel.kt reconciles device BlockedNumberContract against the backend on load and unblock hits both sides. Backend 167/167 tests pass. compileDebugKotlin passes. Merged to develop via PR #46 (bc30c48).
4.3.13 | Admin: User Reports + FP/FN Review + Model Performance pages | 4.3.2, 4.3.4 | Track D (Web Dashboard) | React + Vite, Chart.js | Complete | - | 2026-08-28 | 2026-09-17 | 2026-08-07
4.3.14 | Admin: Registered Users + Export Hub + Server Monitoring + API Logs + DB Storage pages | 1.3.13 | Track D (Web Dashboard) | React + Vite, TanStack Table | Complete | - | 2026-08-28 | 2026-09-17 | 2026-08-07
4.3.15 | Admin: Scam Tips + Settings + Notifications pages | 1.3.13 | Track D (Web Dashboard) | React + Vite | Complete | - | 2026-08-28 | 2026-09-17 | 2026-08-07
4.4 | Test: sprint-level unit and integration testing before demo. [Test] |  | Assigned per WP | Per work-package resources listed below | In Progress | - | 2026-08-28 | 2026-09-17
4.4.1 | Unit test: report intake -> dataset append flow | 4.3.1 | Track A (Backend) | pytest | Not Started | - | 2026-08-28 | 2026-09-17
4.4.2 | Unit test: retraining trigger evaluation logic | 4.3.3 | Track B (AI/ML) | pytest | Complete | - | 2026-08-28 | 2026-09-17 | 2026-08-07
4.4.3 | Integration test: full retraining round trip (report -> validate -> retrain -> deploy) | 4.3.5, 4.3.7 | All members | Full test environment | Not Started | - | 2026-08-28 | 2026-09-17
4.5 | Sprint Review (demo) and Retrospective (lessons learned) at end of Sprint 4. [Review + Retro] |  | All members | Per work-package resources listed below | Not Started | - | 2026-08-28 | 2026-09-17
4.5.1 | Sprint 4 demo (retraining trigger fires end-to-end) | 4.4.3 | All members | Full stack running | Not Started | - | 2026-08-28 | 2026-09-17
4.5.2 | Sprint 4 retrospective |  | All members | Retro board | Not Started | - | 2026-08-28 | 2026-09-17
5 | Sprint 5: Integration, Hardening & Stretch Features |  | All members | Sprint backlog, Chapter 3 pseudocode & mockups | In Progress | - | 2026-09-18 | 2026-10-08 |  | 3-week sprint per Agile Model (Chapter 3)
5.1 | Analysis: refine backlog for Sprint 5, clarify acceptance criteria. [Analysis] |  | All members | Per work-package resources listed below | Not Started | - | 2026-09-18 | 2026-10-08
5.1.1 | Review integration issues surfaced during Sprints 2-4 |  | All members | Bug tracker | Not Started | - | 2026-09-18 | 2026-10-08
5.1.2 | Identify stretch features & remaining tech debt |  | All members | Backlog | Not Started | - | 2026-09-18 | 2026-10-08
5.2 | Design: technical specifications and interface designs for Sprint 5 items. [Design] |  | Assigned per WP | Per work-package resources listed below | Not Started | - | 2026-09-18 | 2026-10-08
5.2.1 | Hardening plan (security + performance) | 5.1.1 | Track A (Backend) | OWASP checklist | Not Started | - | 2026-09-18 | 2026-10-08
5.2.2 | Model refinement plan using S2-S4 collected data | 5.1.1 | Track B (AI/ML) | Collected classification logs | Not Started | - | 2026-09-18 | 2026-10-08
5.3 | Build (development): implement the Sprint 5 work packages. [Build] |  | Assigned per WP | Per work-package resources listed below | In Progress | - | 2026-09-18 | 2026-10-08
5.3.1 | End-to-end integration hardening across all seams |  | All members | Full stack | Not Started | - | 2026-09-18 | 2026-10-08
5.3.2 | API security review + rate limiting | 5.2.1 | Track A (Backend) | @nestjs/throttler | Complete | - | 2026-09-18 | 2026-10-08 | 2026-08-07
5.3.3 | Performance pass on hot paths (classification, dashboard queries) | 5.2.1 | All members | Profiler tools | Not Started | - | 2026-09-18 | 2026-10-08
5.3.4 | Manual retraining trigger endpoint (fallback if auto is unstable) | 4.3.3 | Track A (Backend) | NestJS | Not Started | - | 2026-09-18 | 2026-10-08 |  | Contingency
5.3.5 | XLM-RoBERTa refinement on data collected during S2-S4 | 5.2.2 | Track B (AI/ML) | GPU, dataset from prod | Not Started | - | 2026-09-18 | 2026-10-08
5.3.6 | Re-evaluate HDBSCAN thresholds against real campaign data | 3.3.5 | Track B (AI/ML) | hdbscan library | In Progress | - | 2026-09-18 | 2026-10-08
5.3.7 | Polish SHAP indicator tag dictionary based on observed outputs | 3.3.6 | Track B (AI/ML) | Tag dictionary file | Not Started | - | 2026-09-18 | 2026-10-08
5.3.8 | Mobile bug bash (edge cases, low-end devices, mixed-language) |  | Track C (Mobile) | Range of test devices | Not Started | - | 2026-09-18 | 2026-10-08
5.3.9 | Mobile UI polish based on dogfooding |  | Track C (Mobile) | Design mockups | Not Started | - | 2026-09-18 | 2026-10-08
5.3.10 | (Stretch) Client licensing/payment portal pages | 1.3.13 | Track D (Web Dashboard) | React + Vite, Stripe or mock | Not Started | - | 2026-09-18 | 2026-10-08 |  | Deferrable
5.3.11 | Dashboard UX polish + carryover pages from earlier sprints |  | Track D (Web Dashboard) | React + Vite | Not Started | - | 2026-09-18 | 2026-10-08
5.4 | Test: sprint-level unit and integration testing before demo. [Test] |  | Assigned per WP | Per work-package resources listed below | Not Started | - | 2026-09-18 | 2026-10-08
5.4.1 | Regression pass across all Sprint 1-4 functionality | 5.3.1 | All members | Regression test suite | Not Started | - | 2026-09-18 | 2026-10-08
5.4.2 | Load test: backend + ML service | 5.3.2 | Track A (Backend) | k6 or JMeter | Not Started | - | 2026-09-18 | 2026-10-08
5.4.3 | Cross-device compatibility test (Android 11+) | 5.3.9 | Track C (Mobile) | Test devices | Not Started | - | 2026-09-18 | 2026-10-08
5.5 | Sprint Review (demo) and Retrospective (lessons learned) at end of Sprint 5. [Review + Retro] |  | All members | Per work-package resources listed below | Not Started | - | 2026-09-18 | 2026-10-08
5.5.1 | Sprint 5 demo (hardened, integrated build) | 5.4.1 | All members | Full stack | Not Started | - | 2026-09-18 | 2026-10-08
5.5.2 | Sprint 5 retrospective |  | All members | Retro board | Not Started | - | 2026-09-18 | 2026-10-08
6 | Sprint 6: Testing, Limited Deployment & Defense Readines |  | All members | Sprint backlog, Chapter 3 pseudocode & mockups | Not Started | - | 2026-10-09 | 2026-10-29 |  | 3-week sprint per Agile Model (Chapter 3)
6.1 | Analysis: refine backlog for Sprint 6, clarify acceptance criteria. [Analysis] |  | All members | Per work-package resources listed below | Not Started | - | 2026-10-09 | 2026-10-29
6.1.1 | Recruit 20 UAT participants (general Android users) |  | All members | Recruitment channels | Not Started | - | 2026-10-09 | 2026-10-29 |  | Per Chapter 3 UAT plan
6.1.2 | Recruit 5 expert validators (IT/cybersec/software) |  | All members | Professional network | Not Started | - | 2026-10-09 | 2026-10-29 |  | Per Chapter 3 Expert Validation
6.1.3 | Plan Phase-1 Limited Deployment scope |  | All members | Deployment plan | Not Started | - | 2026-10-09 | 2026-10-29
6.2 | Design: technical specifications and interface designs for Sprint 6 items. [Design] |  | Assigned per WP | Per work-package resources listed below | Not Started | - | 2026-10-09 | 2026-10-29
6.2.1 | UAT session protocol + scenarios | 6.1.1 | All members | UAT script | Not Started | - | 2026-10-09 | 2026-10-29
6.2.2 | Expert Validation protocol | 6.1.2 | All members | Validation script | Not Started | - | 2026-10-09 | 2026-10-29
6.2.3 | Deployment rollout checklist | 6.1.3 | Track A (Backend) | Runbook | Not Started | - | 2026-10-09 | 2026-10-29
6.2.4 | Defense demo storyboard |  | All members | Slide outline | Not Started | - | 2026-10-09 | 2026-10-29
6.3 | Build (development): implement the Sprint 6 work packages. [Build] |  | Assigned per WP | Per work-package resources listed below | Not Started | - | 2026-10-09 | 2026-10-29
6.3.1 | APK signing + release build | 5.3.9 | Track C (Mobile) | Signing key, gradle | Not Started | - | 2026-10-09 | 2026-10-29
6.3.2 | Backend production deployment | 5.2.3 | Track A (Backend) | Production server | Not Started | - | 2026-10-09 | 2026-10-29
6.3.3 | Dashboard production deployment | 5.3.11 | Track D (Web Dashboard) | Production hosting | Not Started | - | 2026-10-09 | 2026-10-29
6.3.4 | Admin credentials issuance (secure) | 6.3.2 | Track A (Backend) | Password manager | Not Started | - | 2026-10-09 | 2026-10-29
6.3.5 | Quick-start guide (PDF) |  | All members | Google Docs / Word | Not Started | - | 2026-10-09 | 2026-10-29
6.3.6 | Defense slide deck | 6.2.4 | All members | PowerPoint / Google Slides | Not Started | - | 2026-10-09 | 2026-10-29
6.4 | Test: sprint-level unit and integration testing before demo. [Test] |  | Assigned per WP | Per work-package resources listed below | Not Started | - | 2026-10-09 | 2026-10-29
6.4.1 | Unit testing (all modules per Chapter 3) |  | All members | pytest, JUnit | Not Started | - | 2026-10-09 | 2026-10-29
6.4.2 | Integration testing across all component seams |  | All members | Full test environment | Not Started | - | 2026-10-09 | 2026-10-29
6.4.3 | System testing: full end-to-end SMS -> output flow | 6.4.2 | All members | Full test environment | Not Started | - | 2026-10-09 | 2026-10-29
6.4.4 | User Acceptance Testing with 20 Android users | 6.1.1, 6.2.1 | All members | Test devices, session forms | Not Started | - | 2026-10-09 | 2026-10-29
6.4.5 | Expert Validation with 5 experts | 6.1.2, 6.2.2 | All members | Session materials | Not Started | - | 2026-10-09 | 2026-10-29
6.4.6 | False Positive/Negative confusion matrix on 20% held-out set | 5.2.5 | Track B (AI/ML) | Validation dataset | Not Started | - | 2026-10-09 | 2026-10-29
6.5 | Sprint Review (demo) and Retrospective (lessons learned) at end of Sprint 6. [Review + Retro] |  | All members | Per work-package resources listed below | Not Started | - | 2026-10-09 | 2026-10-29
6.5.1 | Phase-1 Limited Deployment rollout to test group | 6.3.1, 6.4.4 | All members | Signed APK, test users | Not Started | - | 2026-10-09 | 2026-10-29 |  | Per Chapter 3
6.5.2 | Track precision, recall, F1 in the wild | 6.5.1 | Track B (AI/ML) | Monitoring dashboard | Not Started | - | 2026-10-09 | 2026-10-29
6.5.3 | Live demo rehearsal (3x) | 6.3.6 | All members | Full stack running | Not Started | - | 2026-10-09 | 2026-10-29
6.5.4 | Panel Q&A preparation |  | All members | Q&A prep document | Not Started | - | 2026-10-09 | 2026-10-29
6.5.5 | Final defense | 6.5.3, 6.5.4 | All members | Slide deck, demo | Not Started | - | 2026-10-09 | 2026-10-29 |  | Target: end of Oct 2026